IN THE MATTER OF AN ARBITRATION

BETWEEN

NORTHBRIDGE RENEWABLES LIMITED
(Claimant)

and

MERIDIAN COMPONENTS LIMITED
(Respondent)

WITNESS STATEMENT OF AMELIA HART

Dated 15 July 2026 | Exhibits AH1-AH10

All persons, companies and events in this document are fictional.

# Introduction

| 1. | I am the Chief Financial Officer of Northbridge Renewables Limited (Northbridge), the Claimant in this arbitration. I have held that position since January 2023. |
| --- | --- |
| 2. | I make this statement from matters within my own knowledge, except where I identify another source. Where I refer to company records, I have reviewed those records in the ordinary course of preparing this statement. |
| 3. | Northbridge develops and operates modular solar-generation sites. This dispute concerns Meridian Components Limited's agreement to supply 120 inverter control units for Northbridge's Orchard Vale project. |
| 4. | I was responsible for approving the commercial terms, monitoring payments and managing the financial consequences of any delay to the project. |
| 5. | Unless otherwise stated, references to dates are to 2026 and monetary amounts are expressed in pounds sterling. |
| 6. | The documents exhibited to this statement are true copies taken from Northbridge's records. |

# The supply agreement and delivery timetable

| 7. | During January, Northbridge invited Meridian to quote for control units that had to be installed before commissioning work began on 25 April. |
| --- | --- |
| 8. | I attended the principal commercial calls with Meridian's Sales Director, Daniel Reeve. I repeatedly explained that the installation sequence left little tolerance for delay. |
| 9. | Meridian represented that it had secured the necessary processor components and could meet Northbridge's programme. |
| 10. | On 1 February, Northbridge and Meridian executed a supply agreement for 120 units at a total price of GBP 1,440,000. |
| 11. | The agreement required 40 units to be delivered by 20 March and the remaining 80 units by 10 April. It also required each unit to pass an eight-hour thermal-soak test at 70 degrees Celsius. |
| 12. | I refer to the executed Supply Agreement dated 1 February 2026, exhibited to this statement as AHxx. |
| 13. | The agreement permitted Northbridge to reject non-conforming units and required Meridian to remedy a material failure within five business days after notice. |
| 14. | Northbridge issued its implementing purchase order on 3 February. A copy of Purchase Order NRL-1047 is at exhibit AHxx. |
| 15. | By an email sent on 5 February, Mr Reeve confirmed the two delivery dates and stated that processor allocation was complete. That email and my reply are exhibited together as AHxx. |

# Pre-delivery assurances

| 16. | Northbridge paid the contractual mobilisation payment of GBP 288,000 on 6 February. |
| --- | --- |
| 17. | At a progress meeting on 11 March, Meridian reported that production was on schedule and that the first batch was in final assembly. |
| 18. | The agreed minutes of that meeting record those assurances. I refer to the minutes marked AHxx. |
| 19. | In reliance on those assurances, Northbridge retained the commissioning team for the planned installation window and did not seek an alternative supplier. |

# Meridian's delay

| 20. | On 18 March, two days before the first delivery deadline, Mr Reeve emailed to say that a component shortage would delay the first batch until early April. |
| --- | --- |
| 21. | The 18 March email chain, in which I asked why the shortage had not been disclosed earlier, is exhibited as AH5. |
| 22. | Northbridge treated the delay as serious because the balance of the units was still due by 10 April. |
| 23. | On 25 March, Northbridge sent a formal notice requiring Meridian to provide a recovery plan and confirm cure by 1 April. I refer to that notice of delay as exhibit AHxx. |
| 24. | Meridian did not provide a credible recovery plan by 1 April. It continued to say that the first units would be dispatched shortly. |

# Delivery and quality failures

| 25. | Forty units arrived at Northbridge's Orchard Vale warehouse on 12 April, twenty-three days after the contractual first-batch date. |
| --- | --- |
| 26. | Northbridge's project engineer, Elena Park, commenced incoming inspection on 13 April. |
| 27. | On 16 April, Ms Park emailed me and Meridian to report repeated thermal shutdowns and visible inconsistencies in the processor boards. |
| 28. | That quality-warning email and Meridian's response are exhibited as AHxx. |
| 29. | Northbridge commissioned an independent inspection by Verity Engineering Services. |
| 30. | Verity inspected the batch on 20 and 21 April. Its report dated 22 April found that 31 of the 40 units failed the required thermal-soak test and that the installed processor differed from the approved specification. |
| 31. | I refer to Verity's inspection report dated 22 April, exhibited as AHxx. |
| 32. | No part of the remaining batch of 80 units was delivered by 22 April. |
| 33. | Northbridge gave Meridian an opportunity to propose immediate replacement of the non-conforming units, but Meridian said replacement processors would not be available before June. |

# Termination and mitigation

| 34. | On 30 April, Northbridge terminated the supply agreement for material delay and non-conformity. The termination letter is exhibited as AHxx. |
| --- | --- |
| 35. | Northbridge then purchased replacement controllers from Apex Controls Limited so that installation could resume. |
| 36. | Apex charged GBP 520,000 for 40 expedited replacement units, including expedited freight. Its invoice AC-7782 dated 5 May is exhibited as AHxx. |
| 37. | Northbridge also incurred remobilisation, storage and testing costs. Those losses are addressed in Northbridge's separate quantum evidence. |
| 38. | The replacement units arrived on 18 May and commissioning resumed on 23 May. |

# Conclusion

| 39. | Meridian did not deliver the first batch on time, delivered no second batch, and supplied units that failed the agreed technical requirement. |
| --- | --- |
| 40. | Northbridge relied on Meridian's assurances until the first contractual deadline had nearly expired. |
| 41. | Northbridge acted promptly to inspect the units, give notice, seek cure and mitigate its position. |
| 42. | I confirm that the facts stated in this witness statement are true to the best of my knowledge and belief. |

Signed: /s/ Amelia Hart

Name: Amelia Hart

Date: 15 July 2026